## scheduling-program of works-RES
|  | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Item | Activity | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | Notes
1 | Inception at Dabane | [12 empty] | 1 day w/shop all staff members
2 | Inception at District | [12 empty] | District stakeholder and councilors
3 | Site Establishment-Office in Plumtree- | [12 empty] | 1 office/accomodation | bar: July
4 | Ward inception one day per per ward for 3 wards | [12 empty] | Ward inception one day per per ward for 3 wards | bar: July to Aug
5 | Recrutement and induction of project staff | [12 empty] | Project officer,1 field officer,2 field monitors,1 bookker,2 interns, | bar: July to Aug
6 | Baseline survey including PPHE index and End line Survey | [12 empty] | 1 baseline survey by external consultant.1 Endline survey by external consultant | bar: May to Jun
7 | Community feedback meeting | [12 empty] | 3 meeting at ward level | bar: May to Jun
8 | Beneficiary registration & verification | [12 empty] | registration will be done after baseline | bar: Aug to Sept
9 | Project Database Development | [12 empty] | External consultant to develop project database
10 | Media outreach/journalists visits | [12 empty] | 1x 5 day documentation by 2 consultants. To invite Newsday and Other Media Houses Journalists to the inception | bar: May
11 | Field Monitoring support visits | [12 empty] | Visits to be conducted each month
12 | Identfication / Selection and training of the Complaints handling Committees | [12 empty] | 3 main Committees these will be at ward level | bar: Aug; Jan
13 | Procurement Phase 1- Office Equipment, computers, tablets, motorbikes, | [12 empty] | too be purchased during the first two months of the projects start up date | bar: July
14 | Procurement Phase 2-Construction Equipment-Delivery to Sites | [12 empty] | too be purchased during the three months of the projects start up date | bar: Aug
15 | Procurement of irrigation material for new irrigation schemes | [12 empty] | too be purchased during the first two months of the projects start up date
16 | Procurement - Fodder and horticultureseed packs | [12 empty] | variety - velvet bean 2kg/farmer forage sorghum - 2kg per farmer lablab - 2kg / farmer elephant grass 2kg/ farmer lucern 2kg per farmer
Borehole rehabilitations
17 | Solarisation of boreholes x 2 (one in ward 6 and 1 in ward 8) | [12 empty] | 2 boreholes in ward 6 and 8 these will be done concurrently 20 days continuosly. | bar: Sept
18 | Rehabilitation of 6 Bush Pumps x 6 (1 in ward 6, 2 in ward 8 and 3 in ward 22) | [12 empty] | 3 boreholes done at the same time in the first month, and three boreholes at once the following month | bar: Aug to Sept
Pipeline installations
19 | Pipeline at sand abstraction sites | [12 empty] | using sand abstrction system and solarised | bar: Sept to Nov
20 | Pipelines at solarised boreholes | [12 empty] | 2 borehole to be solarised and a pipeline constructed on | bar: Oct to Dec
21 | Establishment of irrigation schemes | [12 empty] | 2 irrigation schems set up
22 | Construction of gardens (in Ward 6 at Hlabathini borehole and Ward 6 at Ntampani borehole) along pipelines with solarised boreholes | [12 empty] | Solar installation will depand on the borehole perfomance | bar: Oct to Nov
23 | Construction of garden in Ward 22 along pipeline taking from sand abstraction from Tekwane River | [12 empty] | Sand abstraction system | bar: Nov to Dec
24 | construction of bvip toilets at irrigation schemes | [12 empty] | Toilet construction in the gardens will be done during establishment of the garden | bar: Nov to Dec
25 | Seed starter packs distribution | [12 empty] | Fodder and horticulture | bar: Oct to Nov
26 | Field Days (Horticulture/Fodder production) | [12 empty] | Field days will be done during land preration and during vegitative stage | bar: Dec; Mar
Construction of Drinking Troughs
27 | Construction of Drinking Troughs at Boreholes | [12 empty] | 12 drinking troughs | bar: Sept
28 | Construction of drinking troughs for sand abstraction systems | [12 empty] | 9 drinking troughs | bar: Sept to Oct
Trainings
30 | Training of PIT – 1 Day * 14 Sites | [12 empty] | 14 committes(2 borehole sehab sites, 1 garden site, 1 pipeline construction site, in ward 8 its 3 borehole rehab sites, 1 garden site, 1 pipeline constructionm site, in ward 22 its 3 borehole rehab sites, 1 garden site and one pipeline construction site) | bar: July
31 | Leadership Training* 3days* 3schemes | [12 empty] | Leadership trainining at each of the irrigation schemes | bar: Aug to Oct
32 | Training and Demonstrations on production of drought-tolerant forages, hay and home-based feeds * 3days* 3 wards | [12 empty] | Demonstrations on production of drought-tolerant forages, hay and home-based feeds * 3days* 3 wards | bar: Nov
33 | Constitution formulation Training* 2days* 3 schemes + Water and Soil Management Training * 1 day * 3 schemes +Integrated Pest and Soil Fertility Management Training * 1 day * 3 schemes | [12 empty] | 3 trainings per ward | bar: Aug to Sept
34 | Pump and Solar Service, Maintenance and Security Training * 2 days * 3 Wards | [12 empty] | Training to start during the installations | bar: Oct
35 | Farming as a business Training * 3days* 3 schemes + Practical Gardening Training * 2 days* 3 schemes | [12 empty] | All irrigation schemes | bar: Dec
36 | Constitution formulation Training* 2days* 3 schemes + Water and Soil Management Training * 1 day * 3 schemes +Integrated Pest and Soil Fertility Management Training * 1 day * 3 schemes | [12 empty] | Training for all projects | bar: July
37 | Committees and Leadership Training* 3days* 3 schemes | [12 empty] | All irrigation schemes | bar: Aug to Sept
38 | Livestock Management Awareness Training * 3days* 3 wards + Training on livestock and rangeland management * 3days* 3 wards +Tick and Tickborne diseases investigations Trainings* 3 days * 3 Wards | [12 empty] | At ward level | bar: Dec
39 | Training on harvesting and post-harvest techniques* 2 days * 3 Wards | [12 empty] | At ward level and demo plots | bar: May
40 | Demonstrations on Removal of invasive plant species * 1days* 3 wards +Demos on Re-grassing * 1 days* 3 wards | [12 empty] | At ward level | bar: Dec
41 | Vet Ext Officers capacity building Vaccination & Disease Investigation x workshop | [12 empty] | At ward level
42 | Setting Up of Complaints Handling and Feedback Mechanism and Training of the committee * 1 day * 3 Wards | [12 empty] | 1 training per committee at ward level | bar: July to Aug
43 | Water point committees Trainings * 1 day * 28 Sites(16+14) + Water Management Trainings * 1 Day * 14 Sites | [12 empty] | 28 commitees training will be conducted at ward level | bar: Nov
44 | CBM, User fund and Maintenance Training for all users * 2 days * 14 Sites | [12 empty] | 14 sites trained trainings | bar: Aug
45 | Participatory Health and Hygiene Education (PHHE) training* 3 days * 3 Wards | [12 empty] | At ward level | bar: Dec
46 | Training and capacity building for health club members* 3 days * Wards | [12 empty] | At ward level | bar: Apr
47 | Demonstrations on fodder and home-based feed production | [12 empty] | At ward level
48 | Monthly Monitoring visits | [12 empty] | to monitor the progress of the project asper the target
49 | Quartely Community Review meetings | [12 empty] | Community to review project progress and make recommendations
50 | Health Clubs Competitions * 3 Wards | [12 empty] | to dertemine the PHHE index | bar: Apr
51 | Progress reporting | [12 empty] | Monthly reporting at Dabane required
52 | Project Audit | [12 empty] | at the end of the project | bar: Jun
53 | Close out Meeting (District level) | [12 empty] | meeting to close the meetinmg | bar: Jun
Note on O2: Joyce: please ensutere tahte ach of these lines are filled up